## Progress Status - STS (2)
RARE TESTING PHASE I
See Below the below table for Progress and RAG Legends
| Period Highlight: | [6 empty] | 11 | [7 empty] | Period Highlight:
ACTIVITY * | WBS | PREDECESSOR | PLAN START DAY | PLAN DURATION DAY | ACTUAL START DATE | ACTUAL DURATION DAY | % Complete & RAG | Ownership | Status | Planned Start Date | Planned End Date | Revised Start Date | Revised End Date | Actual Finish Datte | Comments
|  |  |  | DURATION | START | DURATION | COMPLETE | [8 empty] | PERIODS
|  |  |  | Week | Week | Week | time axis 2019-08-05 to 2019-12-31
 | time axis 2019-08-05 to 2019-12-31
GENERIC
Workspaces & Workstations | 1 |  | 1 | 5 | 1 | 9 | 90% | Vijay/Pradeep | WIP | 2019-08-05 | 2019-08-09 |  |  |  | Mouse Over
Softwares Installation in Workstations (Java JDK 8.0, Eclipse IDE, Maven, Notepad ++, Putty, Filezilla, Oracle SQL Developer, DB2, SOAPUI) | 2 |  | 2 | 5 | 2 | 8 | 100% | Vijay/Pradeep/Maveric Team | Completed | 2019-08-06 | 2019-08-12 |  |  |  | Mouse Over
VPN Connectivity | 3 |  | 2 | 5 | 2 | 9 | 100% | Vijay/Pradeep/Maveric Team | Completed | 2019-08-06 | 2019-08-12 |  |  |  | Mouse Over
Overview of RARE Testing DOTOPAL | 4 |  | 1 | 5 | 1 | 5 | 100% | Naren, Madesh Team | Completed | 2019-08-05 | 2019-08-09 |  |  |  | Mouse Over
Overview of RARE Testing STS | 5 |  | 1 | 5 | 1 | 5 | 100% | Naren, Vinod Balaji | Completed | 2019-08-05 | 2019-08-09 |  |  |  | Mouse Over
Current Coverage of RARE For STS (Inclusive of Workflow/Sub-workflow) | 6 |  | 2 | 3 | 2 | 3 | 100% | Magesh, Naren | Completed
Current Coverage of RARE For DOTOPAL (Inclusive of Workflow/Sub-workflow) | 7 |  | 4 | 3 | 4 | 3 | 100% | Magesh, Naren | Completed
PRODUCTION DATA SOURCE (for STS) - SG & IN
Prod Dump with all Touch points and CH - Faster Payment | 100 |  | 6 | 5 | 6 | 10 | 0% | PJ Vinod/Vinod Balaji/Naren | [6 empty] | Mouse Over
Prod Dump with all Touch points and CH -BTC | 101 |  | 16 | 5 |  |  |  | PJ Vinod/Vinod Balaji/Naren | [6 empty] | Mouse Over
Prod Dump with all Touch points and CH - TT | 102 |  | 21 | 5 |  |  |  | PJ Vinod/Vinod Balaji/Naren | [6 empty] | Mouse Over
Prod Dump with all Touch points and CH - TAX | 103 |  | 21 | 5 |  |  |  | PJ Vinod/Vinod Balaji/Naren | [6 empty] | Mouse Over
Prod Dump with all Touch points and CH - RTGS | 104 |  | 26 | 5 |  |  |  | PJ Vinod/Vinod Balaji/Naren | [6 empty] | Mouse Over
Prod Dump with all Touch points and CH - ACH | 105 |  | 26 | 5 |  |  |  | PJ Vinod/Vinod Balaji/Naren | [6 empty] | Mouse Over
Prod Dump with all Touch points and CH - PAY | 106 |  | 36 | 5 |  |  |  | PJ Vinod/Vinod Balaji/Naren | [6 empty] | Mouse Over
Prod Dump with all Touch points and CH - All Converted Payment | 107 |  | 36 | 5 |  |  |  | PJ Vinod/Vinod Balaji/Naren | [6 empty] | Mouse Over
INFRASTRUCTURE (for STS)
STS Test Evironment Access and Setup | 200 |  | 11 | 5 | 11 | 5 | 0% | STS Dev/Naren/Renish/Ram/Vinod | [6 empty] | Mouse Over
Database Setup for Staging | 201 |  | 11 | 10 | 11 | 5 | 0% | STS Dev/Naren/Renish/Ram/Madesh | [6 empty] | Mouse Over
Automation Environment for the Tool & Stubs (Citrus) | 204 |  | 16 | 5 |  |  |  | STS Dev/Naren/Renish/Ram/Vinod | [6 empty] | Mouse Over
FLOW IDENTIFICATION (for STS)
KT - Session & Functional Flow - Faster Payments | 300 |  | 6 | 40 | 6 | 10 | 12% | Vinod Balaji/Magesh/Niranjan | [6 empty] | Mouse Over
KT - Session & Functional Flow - BTC
KT - Session & Functional Flow - TT
KT - Session & Functional Flow - TAX
KT - Session & Functional Flow - RTGS
KT - Session & Functional Flow - ACH
KT - Session & Functional Flow - PAY
KT - Session & Functional Flow - All Converted Payments
FLOW IDENTIFICATION (for STS)
Identifying major flows in Product 1 - Faster Payment | 301 | 100, 300 | 6 | 10 | 6 | 10 | 50% | Magesh / Niranjan | [6 empty] | Mouse Over
Identifying major flows in Product 2 - BTC | 302 | 101, 300 | 11 | 5 |  |  |  | Magesh / Niranjan | [6 empty] | Mouse Over
Identifying major flows in Product 3 - TT | 303 | 102, 300 | 21 | 5 |  |  |  | Magesh / Niranjan | [6 empty] | Mouse Over
Identifying major flows in Product 4 - TAX | 304 | 103, 300 | 26 | 5 |  |  |  | Magesh / Niranjan | [6 empty] | Mouse Over
Identifying major flows in Product 5 - RTGS | 305 | 104, 300 | 31 | 5 |  |  |  | Magesh / Niranjan | [6 empty] | Mouse Over
Identifying major flows in Product 6 - ACH | 306 | 105, 300 | 36 | 5 |  |  |  | Magesh / Niranjan | [6 empty] | Mouse Over
Identifying major flows in Product 7 - PAY | 307 | 106, 300 | 41 | 5 |  |  |  | Magesh / Niranjan | [6 empty] | Mouse Over
Identifying major flows in Product 8 - All Converted Payments | 308 | 107, 300 | 46 | 5 |  |  |  | Magesh / Niranjan | [6 empty] | Mouse Over
STAGING (for STS)
Development of XML Sorting and XML validation | 400 |  | 11 | 15 |  |  |  | Nagaraj | [6 empty] | Mouse Over
Development of pushing XML's to Test DB | 401 |  | 16 | 15 |  |  |  | Nagaraj | [6 empty] | Mouse Over
Message sorting / Masking - Faster Payments | 402 | 100 | 26 | 5 |  |  |  | Nagaraj, Mohan, Gopi | [6 empty] | Mouse Over
Message sorting / Masking - BTC | 403 | 102 | 31 | 5 |  |  |  | Nagaraj, Mohan, Gopi | [6 empty] | Mouse Over
Message sorting / Masking - TT | 404 | 103 | 36 | 5 |  |  |  | Nagaraj, Mohan, Gopi | [6 empty] | Mouse Over
Message sorting / Masking - TAX | 405 | 104 | 41 | 5 |  |  |  | Nagaraj, Mohan, Gopi | [6 empty] | Mouse Over
Message sorting / Masking - RTGS | 406 | 105 | 46 | 5 |  |  |  | Nagaraj, Mohan, Gopi | [6 empty] | Mouse Over
Message sorting / Masking - Product 6 (TBD) | 407 | 106 | 51 | 5 |  |  |  | Nagaraj, Mohan, Gopi | [6 empty] | Mouse Over
Message sorting / Masking - Product 7 (TBD) | 408 | 107 | 56 | 5 |  |  |  | Nagaraj, Mohan, Gopi | [6 empty] | Mouse Over
Message sorting / Masking - Product 8 (TBD) | 409 | 108 | 61 | 5 |  |  |  | Nagaraj, Mohan, Gopi | [6 empty] | Mouse Over
DashBoard creation for the Sorting Done | 410 | 107, 308 | 66 | 5 |  |  |  | Nagaraj, Mohan, Gopi | [6 empty] | Mouse Over
AUTOMATION (for STS)
Table Creation for Automation | 500 |  | 7 | 2 | 7 | 3 | 70% | Renish / Lakshmi / Madesh | [6 empty] | Mouse Over
POC - Citrus Framework - Pushing / Testing | 501 |  | 11 | 10 | 11 | 5 | 40% | Shenilton/Renish | [6 empty] | Mouse Over
POC - Citrus Framework - Simulator - API | 502 |  | 16 | 5 |  |  |  | Shenilton/Renish | [6 empty] | Mouse Over
POC - Citrus Framework - Simulator - EDMI JMS | 503 |  | 21 | 5 |  |  |  | Shenilton/Renish | [6 empty] | Mouse Over
POC - Citrus Framework - Simulator - MQ | 504 |  | 21 | 5 |  |  |  | Shenilton/Renish | [6 empty] | Mouse Over
POC - Citrus Framework - Simulator - Solace | 505 |  | 21 | 5 |  |  |  | Shenilton/Renish | [6 empty] | Mouse Over
RARE Simulation - Faster Payments | 513 | 506, 507, 510 | 41 | 5 |  |  |  | Naren & Team | [6 empty] | Mouse Over
RARE Simulation - Product 2 (TBD) | 514 |  | 46 | 5 |  |  |  | Naren & Team | [6 empty] | Mouse Over
RARE Simulation - Product 3 (TBD) | 515 |  | 46 | 5 |  |  |  | Naren & Team | [6 empty] | Mouse Over
RARE Simulation - Product 4 (TBD) | 516 |  | 51 | 5 |  |  |  | Naren & Team | [6 empty] | Mouse Over
RARE Simulation - Product 5 (TBD) | 517 |  | 51 | 5 |  |  |  | Naren & Team | [6 empty] | Mouse Over
RARE Simulation - Product 6 (TBD) | 518 |  | 56 | 5 |  |  |  | Naren & Team | [6 empty] | Mouse Over
RARE Simulation - Product 7 (TBD) | 519 |  | 56 | 5 |  |  |  | Naren & Team | [6 empty] | Mouse Over
RARE Simulation - Product 8 (TBD) | 520 |  | 61 | 5 |  |  |  | Naren & Team | [6 empty] | Mouse Over
Report DashBoard for STS
POC - DashBoard Using Kibanna, Grafanna | 600 | 301 -308, 500-520 | 36 | 10 |  |  |  | Renish/Naren/Shenilton | [6 empty] | Mouse Over
Creation of DashBoard- Comprises of Test Summary - #Transactions Input, #Matches, #UnMatched Count & Pattern coverage - No of products, workflows tested using producton cut & Transaction coverage - No of critical scenarios tested using production cut | 601 | 301 -308, 500-520 | 46 | 30 |  |  |  | Renish/Naren/Shenilton | [6 empty] | Mouse Over
EXECUTIONS (for STS)
Full Execution of RARE for 8 Products | 701 | 501-520 | 76 | 5 |  |  |  | Naren & Team
DashBoard Showing the Execution Report | 702 | 601 | 79 | 3 |  |  |  | Naren & Team
* All activities listed above are high level and internal sub activities dependent on the parent activity is not listed
** Solution will be developed for 5 Model countries
Plan |  | R | Slipped from planned Completion date and high impact Activities which could go beyond the target/revised target date based on the dependency with other parties & current progress
Actual |  | A | Activities which are dependent on other activity and still can be achieved with the target date
% Completed |  | G | Activities that are completed Slipped from planned completion date and doesn't have much impact on any other activities (workaround available)
Actual Completion (Beyond Plan) |  | W | Activities which are Yet to Start and not foreseen any impact on meeting the target date
% Complete (beyond plan
Note on S10: Ram <22/08>: Workspace Workspace to be identified for three more resources. At presentt resources are managing with the space available in PCT. Vijay to action it to identify workspace.
Note on S11: Ram:<22/08> One resource have JDK version issue and ETA to resolve on 26/08. Ticket raised
Note on S12: Ram<22/08>: VPN connectivity approval pending for one resource as the approval in Auto approval Queue. However, this doesn't affect the work of the resource.
Note on S13: Ram<22/08> Detailed overview of RARE completed with Automation team of DOTOPAL
Note on S18: RAM <22/08> PJ Vinod had requested for the Production Data Dump for faster payments inclusive of all touch points, PSS Team to revert to them. This is significantly delaying our progress.
Note on S27: Ram <22/08>: Currently no instances are free or available in STS Environment to make alterations to the routing and /or stubbing without disturbing existing teams. Creating a new instance is a challenge as it requires hardware in the server may to be increased like RAM size, Storage and the implementation would also take time. This is now completely a blocker for STUB creation
Note on S28: Ram: <22/08> During the discussion with STS development, they have mentioned it would require many topics, since most of the countries while responding to the request will post their request in their respective country topics. Discussion would held next week to check if there is any possibility to have few topics to route traffic. At the moment this is also a blocker for STUB creation
Note on S31: Ram<22/08> Faster Payments Functional flow completed, received the input files and tables to refer after posting the transactions. At present the team is very busy in Regression test execution for the release. Requested Vinod Balaji to provide atleast 1 hour of their SPOC time to share information with Maveric SME's and Automation team
Note on S40: Ram <22/08>: Functionally understood the flow and the touch points between all the systems. Automation Team, not able to create extraction scripts for Data extraction and sorting
Note on S61: Kozhithottathill, Renish: <20/08>Jira raised by Lakshmi. Schema has been created by DB Team in DB2. <21/08> Table structure has been sent to Madesh & Lakshmi. Awaiting table creation
Note on S62: Ram<22/08>: Java scripts developed for Read XML and Capture data in XL, Code developed to read log from log server. Awaiting server access to deploy services. Code Development completed to two XML files.

## Progress Status - STS
RARE TESTING PHASE I - With DownStream Systems Connectivity
See Below the below table for Progress and RAG Legends
| Period Highlight: | [6 empty] | 16 | [7 empty] | Period Highlight:
ACTIVITY * | WBS | PREDECESSOR | PLAN START DAY | PLAN DURATION DAY | ACTUAL START DATE | ACTUAL DURATION DAY | % Complete & RAG | Ownership | Status | Planned Start Date | Planned End Date | Revised Start Date | Revised End Date | Actual Finish Date | Comments
|  |  |  | DURATION | START | DURATION | COMPLETE | [8 empty] | PERIODS
|  |  |  | Week | Week | Week | time axis 2019-08-05 to 2019-12-31
 | time axis 2019-08-05 to 2019-12-31
GENERIC
Workspaces & Workstations | 1 |  | 1 | 5 | 1 | 9 | 90% | Vijay/Pradeep | WIP | 2019-08-05 | 2019-08-09 |  |  |  | Mouse Over
Softwares Installation in Workstations (Java JDK 8.0, Eclipse IDE, Maven, Notepad ++, Putty, Filezilla, Oracle SQL Developer, DB2, SOAPUI) | 2 |  | 2 | 5 | 2 | 8 | 100% | Vijay/Pradeep/Maveric Team | Completed | 2019-08-06 | 2019-08-12 |  |  |  | Mouse Over
VPN Connectivity | 3 |  | 2 | 5 | 2 | 9 | 100% | Vijay/Pradeep/Maveric Team | Completed | 2019-08-06 | 2019-08-12 |  |  |  | Mouse Over
Overview of RARE Testing DOTOPAL | 4 |  | 1 | 5 | 1 | 5 | 100% | Naren, Madesh Team | Completed | 2019-08-05 | 2019-08-09 |  |  |  | Mouse Over
Overview of RARE Testing STS | 5 |  | 1 | 5 | 1 | 5 | 100% | Naren, Vinod Balaji | Completed | 2019-08-05 | 2019-08-09 |  |  |  | Mouse Over
Current Coverage of RARE For STS (Inclusive of Workflow/Sub-workflow) | 6 |  | 2 | 3 | 2 | 3 | 100% | Magesh, Naren | Completed | 2019-08-06 | 2019-08-09
Current Coverage of RARE For DOTOPAL (Inclusive of Workflow/Sub-workflow) | 7 |  | 4 | 3 | 4 | 3 | 100% | Magesh, Naren | Completed | 2019-08-06 | 2019-08-09
Identification of Product for Baseframework Development | 9 | [5 empty] | 100% | Vinod Balaji/Ram/Naren | Completed | 2019-08-12 | 2019-08-12
Prioritisation of STS Products for RARE Testing | 8 | [5 empty] | 100% | Vinod Balaji/Ram | Completed | 2019-08-24 | 2019-08-24
INFRASTRUCTURE (for STS)
STS Test Evironment Access and Setup | 100 |  | 11 | 5 | 11 | 5 | 50% | Naren/Renish/Ram/Vinod | [6 empty] | Mouse Over
Schema Creation and Table Setup for Staging | 101 |  | 11 | 10 | 11 | 5 | 100% | Naren/Renish/Ram/Madesh | [6 empty] | Mouse Over
Automation Environment for the Tool & Stubs (Citrus) | 102 | [5 empty] | 5% | Naren/Renish/Ram/Vinod | [6 empty] | Mouse Over
Access to Log Server/ Log Reader Service Deployment | 103 | [5 empty] | 50% | Sheniltion/PJ Vinod/Vinod Balaji
DEVELOPMENT - STAGING FRAMEWORK
Staging - Extraction of XML's | 200 | 500, 600, 700,800,900,1000,1100, 1200 | [5 empty] | Renish/Naren/Shenilton | [6 empty] | Mouse Over
Staging - Message Identifier | 201 | [6 empty] | Renish/Naren/Shenilton | [6 empty] | Mouse Over
Staging - Stiching of Messages across all touch points | 202 | [6 empty] | Renish/Naren/Shenilton | [6 empty] | Mouse Over
Staging - Pattern Identification | 203 | [6 empty] | Renish/Naren/Shenilton | [6 empty] | Mouse Over
Staging - Masking | 204 | [6 empty] | Renish/Naren/Shenilton | [6 empty] | Mouse Over
DashBoard creation for the Sorting Done | 205 | [6 empty] | Renish/Naren/Shenilton | [6 empty] | Mouse Over
DEVELOPMENT - AUTOMATION FRAMEWORK
POC - Citrus Framework - Pushing / Testing | 300 | [6 empty] | Naren & Team
POC - Citrus Framework - Simulator - API | 301 | [6 empty] | Naren & Team
POC - Citrus Framework - Simulator - EDMI JMS | 302 | [6 empty] | Naren & Team
POC - Citrus Framework - Simulator - MQ | 303 | [6 empty] | Naren & Team
POC - Citrus Framework - Simulator - Solace | 304 | [6 empty] | Naren & Team
Log Comparison | 305 | [6 empty] | Naren & Team
DEVELOPMENT - RARE DASHBOARD
POC - DashBoard Using Kibanna, Grafanna | 400 | [6 empty] | Renish/Naren/Shenilton | [6 empty] | Mouse Over
Creation of DashBoard- Comprises of Test Summary - #Transactions Input, #Matches, #UnMatched Count & Pattern coverage - No of products, workflows tested using producton cut & Transaction coverage - No of critical scenarios tested using production cut | 401 | 510,610, 710,810, 910, 1010, 1110, 1210 | [5 empty] | Renish/Naren/Shenilton | [6 empty] | Mouse Over
FASTER PATYMENTS (Singapore & India)
Prod Dump with all Touch points | 500 | [5 empty] | 50% | PJ Vinod/Vinod Balaji/Ram | [6 empty] | Mouse Over
KT - Session & Functional Flow | 501 | [6 empty] | PJ Vinod/Vinod Balaji/Magesh/Niranjan | [6 empty] | Mouse Over
Table & Schema to Validate | 502 | [6 empty] | Naren & Team
Identifying major flows in Faster Payment | 503 | [6 empty] | Magesh/Niranjan | [6 empty] | Mouse Over
Country Specific Deviations | 504 | [6 empty] | Vinod Balaji/Magesh/Niranjan/Ram | [6 empty] | Mouse Over
Masking & Data to change in the Input Files | 505 | 500 | [5 empty] | Naren & Team
Analyse & Document of Pattern Identification from XML's | 506 | 500 | [5 empty] | Magesh/Niranjan
Staging - Extraction of XML's | 507 | 500200 | [5 empty] | Naren & Team | [6 empty] | Mouse Over
Staging - Message Identifier | 508 | 501201 | [5 empty] | Naren & Team | [6 empty] | Mouse Over
Staging - Stiching of Messages across all touch points | 509 | 501202 | [5 empty] | Naren & Team | [6 empty] | Mouse Over
Staging - Pattern Identification | 510 | 506203 | [5 empty] | Naren & Team | [6 empty] | Mouse Over
Staging - Masking | 511 | 505204 | [5 empty] | Naren & Team
Test Preparation | 512 | 500-511 | [5 empty] | Naren & Team
Smoke Test 1000 Files - FP (Singapore & India) | 513 | 300-304 | [5 empty] | Naren & Team
Validation of Results (Through Log files comparison) | 514 | 513, 305 | [5 empty] | Naren & Team
Smoke Test Results | 515 | 513-515, 400-401 | [5 empty] | Naren & Team
Book Transfer & Cheques (Singapore & India)
Prod Dump with all Touch points | 600 | [6 empty] | PJ Vinod/Vinod Balaji/Ram | [6 empty] | Mouse Over
KT - Session & Functional Flow | 601 | [6 empty] | PJ Vinod/Vinod Balaji/Magesh/Niranjan | [6 empty] | Mouse Over
Table & Schema to Validate | 602 | [6 empty] | Naren & Team
Identifying major flows in Faster Payment | 603 | [6 empty] | Magesh/Niranjan | [6 empty] | Mouse Over
Country Specific Deviations | 604 | [6 empty] | Vinod Balaji/Magesh/Niranjan/Ram | [6 empty] | Mouse Over
Masking & Data to change in the Input Files | 605 | 600 | [5 empty] | Naren & Team
Analyse & Document of Pattern Identification from XML's | 606 | 600 | [5 empty] | Magesh/Niranjan
Staging - Extraction of XML's | 607 | 600200 | [5 empty] | Naren & Team | [6 empty] | Mouse Over
Staging - Message Identifier | 608 | 601201 | [5 empty] | Naren & Team | [6 empty] | Mouse Over
Staging - Stiching of Messages across all touch points | 609 | 601202 | [5 empty] | Naren & Team | [6 empty] | Mouse Over
Staging - Pattern Identification | 610 | 606203 | [5 empty] | Naren & Team | [6 empty] | Mouse Over
Staging - Masking | 611 | 605204 | [5 empty] | Naren & Team
Test Preparation | 612 | 600- 611 | [5 empty] | Naren & Team
Smoke Test 1000 Files - FP (Singapore & India) | 613 | 300-304 | [5 empty] | Naren & Team
Validation of Results (Through Log files comparison) | 614 | 613, 305 | [5 empty] | Naren & Team
Smoke Test Results | 615 | 613-615 400-401 | [5 empty] | Naren & Team
Telegraphic Transfer (Singapore & India)
Prod Dump with all Touch points | 700 | [6 empty] | PJ Vinod/Vinod Balaji/Ram | [6 empty] | Mouse Over
KT - Session & Functional Flow | 701 | [6 empty] | PJ Vinod/Vinod Balaji/Magesh/Niranjan | [6 empty] | Mouse Over
Table & Schema to Validate | 702 | [6 empty] | Naren & Team
Identifying major flows in Faster Payment | 703 | [6 empty] | Magesh/Niranjan | [6 empty] | Mouse Over
Country Specific Deviations | 704 | [6 empty] | Vinod Balaji/Magesh/Niranjan/Ram | [6 empty] | Mouse Over
Masking & Data to change in the Input Files | 705 | 700 | [5 empty] | Naren & Team
Analyse & Document of Pattern Identification from XML's | 706 | 700 | [5 empty] | Magesh/Niranjan
Staging - Extraction of XML's | 707 | 700200 | [5 empty] | Naren & Team | [6 empty] | Mouse Over
Staging - Message Identifier | 708 | 701201 | [5 empty] | Naren & Team | [6 empty] | Mouse Over
Staging - Stiching of Messages across all touch points | 709 | 701202 | [5 empty] | Naren & Team | [6 empty] | Mouse Over
Staging - Pattern Identification | 710 | 706203 | [5 empty] | Naren & Team | [6 empty] | Mouse Over
Staging - Masking | 711 | 705204 | [5 empty] | Naren & Team
Test Preparation | 712 | 700- 611 | [5 empty] | Naren & Team
Smoke Test 1000 Files - FP (Singapore & India) | 713 | 300-304 | [5 empty] | Naren & Team
Validation of Results (Through Log files comparison) | 714 | 713, 305 | [5 empty] | Naren & Team
Smoke Test Results | 715 | 713-715 400-401 | [5 empty] | Naren & Team
RTGS (Singapore & India)
Prod Dump with all Touch points | 800 | [6 empty] | PJ Vinod/Vinod Balaji/Ram | [6 empty] | Mouse Over
KT - Session & Functional Flow | 801 | [6 empty] | PJ Vinod/Vinod Balaji/Magesh/Niranjan | [6 empty] | Mouse Over
Table & Schema to Validate | 802 | [6 empty] | Naren & Team
Identifying major flows in Faster Payment | 803 | [6 empty] | Magesh/Niranjan | [6 empty] | Mouse Over
Country Specific Deviations | 804 | [6 empty] | Vinod Balaji/Magesh/Niranjan/Ram | [6 empty] | Mouse Over
Masking & Data to change in the Input Files | 805 | 800 | [5 empty] | Naren & Team
Analyse & Document of Pattern Identification from XML's | 806 | 800 | [5 empty] | Magesh/Niranjan
Staging - Extraction of XML's | 807 | 800200 | [5 empty] | Naren & Team | [6 empty] | Mouse Over
Staging - Message Identifier | 808 | 801201 | [5 empty] | Naren & Team | [6 empty] | Mouse Over
Staging - Stiching of Messages across all touch points | 809 | 801202 | [5 empty] | Naren & Team | [6 empty] | Mouse Over
Staging - Pattern Identification | 810 | 806203 | [5 empty] | Naren & Team | [6 empty] | Mouse Over
Staging - Masking | 811 | 805204 | [5 empty] | Naren & Team
Test Preparation | 812 | 800- 611 | [5 empty] | Naren & Team
Smoke Test 1000 Files - FP (Singapore & India) | 813 | 300-304 | [5 empty] | Naren & Team
Validation of Results (Through Log files comparison) | 814 | 813, 305 | [5 empty] | Naren & Team
Smoke Test Results | 815 | 813-815 400-401 | [5 empty] | Naren & Team
TAX (Singapore & India)
Prod Dump with all Touch points | 900 | [6 empty] | PJ Vinod/Vinod Balaji/Ram | [6 empty] | Mouse Over
KT - Session & Functional Flow | 901 | [6 empty] | PJ Vinod/Vinod Balaji/Magesh/Niranjan | [6 empty] | Mouse Over
Table & Schema to Validate | 902 | [6 empty] | Naren & Team
Identifying major flows in Faster Payment | 903 | [6 empty] | Magesh/Niranjan | [6 empty] | Mouse Over
Country Specific Deviations | 904 | [6 empty] | Vinod Balaji/Magesh/Niranjan/Ram | [6 empty] | Mouse Over
Masking & Data to change in the Input Files | 905 | 900 | [5 empty] | Naren & Team
Analyse & Document of Pattern Identification from XML's | 906 | 900 | [5 empty] | Magesh/Niranjan
Staging - Extraction of XML's | 907 | 900200 | [5 empty] | Naren & Team | [6 empty] | Mouse Over
Staging - Message Identifier | 908 | 901201 | [5 empty] | Naren & Team | [6 empty] | Mouse Over
Staging - Stiching of Messages across all touch points | 909 | 901202 | [5 empty] | Naren & Team | [6 empty] | Mouse Over
Staging - Pattern Identification | 910 | 906203 | [5 empty] | Naren & Team | [6 empty] | Mouse Over
Staging - Masking | 911 | 905204 | [5 empty] | Naren & Team
Test Preparation | 912 | 900- 611 | [5 empty] | Naren & Team
Smoke Test 1000 Files - FP (Singapore & India) | 913 | 300-304 | [5 empty] | Naren & Team
Validation of Results (Through Log files comparison) | 914 | 913, 305 | [5 empty] | Naren & Team
Smoke Test Results | 915 | 913-915 400-401 | [5 empty] | Naren & Team
ACH (Singapore & India)
Prod Dump with all Touch points | 1000 | [6 empty] | PJ Vinod/Vinod Balaji/Ram | [6 empty] | Mouse Over
KT - Session & Functional Flow | 1001 | [6 empty] | PJ Vinod/Vinod Balaji/Magesh/Niranjan | [6 empty] | Mouse Over
Table & Schema to Validate | 1002 | [6 empty] | Naren & Team
Identifying major flows in Faster Payment | 1003 | [6 empty] | Magesh/Niranjan | [6 empty] | Mouse Over
Country Specific Deviations | 1004 | [6 empty] | Vinod Balaji/Magesh/Niranjan/Ram | [6 empty] | Mouse Over
Masking & Data to change in the Input Files | 1005 | 1000 | [5 empty] | Naren & Team
Analyse & Document of Pattern Identification from XML's | 1006 | 1000 | [5 empty] | Magesh/Niranjan
Staging - Extraction of XML's | 1007 | 1000200 | [5 empty] | Naren & Team | [6 empty] | Mouse Over
Staging - Message Identifier | 1008 | 1001201 | [5 empty] | Naren & Team | [6 empty] | Mouse Over
Staging - Stiching of Messages across all touch points | 1009 | 1001202 | [5 empty] | Naren & Team | [6 empty] | Mouse Over
Staging - Pattern Identification | 1010 | 1006203 | [5 empty] | Naren & Team | [6 empty] | Mouse Over
Staging - Masking | 1011 | 1005204 | [5 empty] | Naren & Team
Test Preparation | 1012 | 1000- 1011 | [5 empty] | Naren & Team
Smoke Test 1000 Files - FP (Singapore & India) | 1013 | 300-304 | [5 empty] | Naren & Team
Validation of Results (Through Log files comparison) | 1014 | 1013, 305 | [5 empty] | Naren & Team
Smoke Test Results | 1015 | 1013-1015 400-401 | [5 empty] | Naren & Team
PAY (Singapore & India)
Prod Dump with all Touch points | 1100 | [6 empty] | PJ Vinod/Vinod Balaji/Ram | [6 empty] | Mouse Over
KT - Session & Functional Flow | 1101 | [6 empty] | PJ Vinod/Vinod Balaji/Magesh/Niranjan | [6 empty] | Mouse Over
Table & Schema to Validate | 1102 | [6 empty] | Naren & Team
Identifying major flows in Faster Payment | 1103 | [6 empty] | Magesh/Niranjan | [6 empty] | Mouse Over
Country Specific Deviations | 1104 | [6 empty] | Vinod Balaji/Magesh/Niranjan/Ram | [6 empty] | Mouse Over
Masking & Data to change in the Input Files | 1105 | 1100 | [5 empty] | Naren & Team
Analyse & Document of Pattern Identification from XML's | 1106 | 1100 | [5 empty] | Magesh/Niranjan
Staging - Extraction of XML's | 1107 | 1100200 | [5 empty] | Naren & Team | [6 empty] | Mouse Over
Staging - Message Identifier | 1108 | 1101201 | [5 empty] | Naren & Team | [6 empty] | Mouse Over
Staging - Stiching of Messages across all touch points | 1109 | 1101202 | [5 empty] | Naren & Team | [6 empty] | Mouse Over
Staging - Pattern Identification | 1110 | 1106203 | [5 empty] | Naren & Team | [6 empty] | Mouse Over
Staging - Masking | 1111 | 1105204 | [5 empty] | Naren & Team
Test Preparation | 1112 | 1100- 611 | [5 empty] | Naren & Team
Smoke Test 1000 Files - FP (Singapore & India) | 1113 | 300-304 | [5 empty] | Naren & Team
Validation of Results (Through Log files comparison) | 1114 | 1113, 305 | [5 empty] | Naren & Team
Smoke Test Results | 1115 | 1113-1115 400-401 | [5 empty] | Naren & Team
All Converted Payments (Singapore & India)
Prod Dump with all Touch points | 1200 | [6 empty] | PJ Vinod/Vinod Balaji/Ram | [6 empty] | Mouse Over
KT - Session & Functional Flow | 1201 | [6 empty] | PJ Vinod/Vinod Balaji/Magesh/Niranjan | [6 empty] | Mouse Over
Table & Schema to Validate | 1202 | [6 empty] | Naren & Team
Identifying major flows in Faster Payment | 1203 | [6 empty] | Magesh/Niranjan | [6 empty] | Mouse Over
Country Specific Deviations | 1204 | [6 empty] | Vinod Balaji/Magesh/Niranjan/Ram | [6 empty] | Mouse Over
Masking & Data to change in the Input Files | 1205 | 1200 | [5 empty] | Naren & Team
Analyse & Document of Pattern Identification from XML's | 1206 | 1200 | [5 empty] | Magesh/Niranjan
Staging - Extraction of XML's | 1207 | 1200200 | [5 empty] | Naren & Team | [6 empty] | Mouse Over
Staging - Message Identifier | 1208 | 1201201 | [5 empty] | Naren & Team | [6 empty] | Mouse Over
Staging - Stiching of Messages across all touch points | 1209 | 1201202 | [5 empty] | Naren & Team | [6 empty] | Mouse Over
Staging - Pattern Identification | 1210 | 1206203 | [5 empty] | Naren & Team | [6 empty] | Mouse Over
Staging - Masking | 1211 | 1205204 | [5 empty] | Naren & Team
Test Preparation | 1212 | 1200- 1211 | [5 empty] | Naren & Team
Smoke Test 1000 Files - FP (Singapore & India) | 1213 | 300-304 | [5 empty] | Naren & Team
Validation of Results (Through Log files comparison) | 1214 | 1213, 305 | [5 empty] | Naren & Team
Smoke Test Results | 1215 | 1213-1215 400-401 | [5 empty] | Naren & Team
Full Execution of RARE for 8 Products | 1300 | 501-520 | 76 | 5 |  |  |  | Naren & Team
DashBoard Showing the Execution Report | 1301 | 601 | 79 | 3 |  |  |  | Naren & Team
* All activities listed above are high level and internal sub activities dependent on the parent activity is not listed
** Solution will be developed for 5 Model countries
Plan |  | R | Slipped from planned Completion date and high impact Activities which could go beyond the target/revised target date based on the dependency with other parties & current progress
Actual |  | A | Activities which are dependent on other activity and still can be achieved with the target date
% Completed |  | G | Activities that are completed Slipped from planned completion date and doesn't have much impact on any other activities (workaround available)
Actual Completion (Beyond Plan) |  | W | Activities which are Yet to Start and not foreseen any impact on meeting the target date
% Complete (beyond plan
Note on S10: Ram <22/08>: Workspace Workspace to be identified for three more resources. At presentt resources are managing with the space available in PCT. Vijay to action it to identify workspace.
Note on S11: Ram:<22/08> One resource have JDK version issue and ETA to resolve on 26/08. Ticket raised
Note on S12: Ram<22/08>: VPN connectivity approval pending for one resource as the approval in Auto approval Queue. However, this doesn't affect the work of the resource.
Note on S13: Ram<22/08> Detailed overview of RARE completed with Automation team of DOTOPAL
Note on S20: Ram <22/08>: Currently no instances are free or available in STS Environment to make alterations to the routing and /or stubbing without disturbing existing teams. Creating a new instance is a challenge as it requires hardware in the server may to be increased like RAM size, Storage and the implementation would also take time. This is now completely a blocker for STUB creation
Note on S21: Kozhithottathill, Renish: <20/08>Jira raised by Lakshmi. Schema has been created by DB Team in DB2. <21/08> Table structure has been sent to Madesh & Lakshmi. Awaiting table creation
Note on S42: RAM <22/08> PJ Vinod had requested for the Production Data Dump for faster payments inclusive of all touch points, PSS Team to revert to them. This is significantly delaying our progress.
Note on S59: RAM <22/08> PJ Vinod had requested for the Production Data Dump for faster payments inclusive of all touch points, PSS Team to revert to them. This is significantly delaying our progress.
Note on S76: RAM <22/08> PJ Vinod had requested for the Production Data Dump for faster payments inclusive of all touch points, PSS Team to revert to them. This is significantly delaying our progress.
Note on S93: RAM <22/08> PJ Vinod had requested for the Production Data Dump for faster payments inclusive of all touch points, PSS Team to revert to them. This is significantly delaying our progress.
Note on S110: RAM <22/08> PJ Vinod had requested for the Production Data Dump for faster payments inclusive of all touch points, PSS Team to revert to them. This is significantly delaying our progress.
Note on S127: RAM <22/08> PJ Vinod had requested for the Production Data Dump for faster payments inclusive of all touch points, PSS Team to revert to them. This is significantly delaying our progress.
Note on S144: RAM <22/08> PJ Vinod had requested for the Production Data Dump for faster payments inclusive of all touch points, PSS Team to revert to them. This is significantly delaying our progress.
Note on S161: RAM <22/08> PJ Vinod had requested for the Production Data Dump for faster payments inclusive of all touch points, PSS Team to revert to them. This is significantly delaying our progress.

## Sheet2 (hidden)
Prod Dump with all Touch points and CH -BTC
Prod Dump with all Touch points and CH - TT
Prod Dump with all Touch points and CH - TAX
Prod Dump with all Touch points and CH - RTGS
Prod Dump with all Touch points and CH - ACH
Prod Dump with all Touch points and CH - PAY
Prod Dump with all Touch points and CH - All Converted Payment