## RARE PLAN
CIB - RARE TESTING FOR DOTOPAL and STS - Technical Plan
# | Solution Component | Sub Components | Activity | Critical Dependency | Owner/Responsibility | Current Status | Target Start Date | Target End Date
1 | Production Dump Analysis |  |  |  | Naren |  | 2019-07-31 | 2019-08-16
|  | Data Collection | Obtain & Analyze Data Collection Points | Automation Team (Gopi Kannan & Gopi Murugan) SPOC for STS and DOTOPAL Dev Team and Contacts (Ram to get SPOC) Dependency on On-boarding & Laptop | Naren | Planned | 2019-07-31 | 2019-08-06
|  |  | Define Data Collection Points |  | Naren | Planned | 2019-08-05 | 2019-08-16
|  | Data Masking | Understand PII fields | SME Support - DOTOPAL and STS | Naren | Reuse for now | 2019-07-31 | 2019-08-02
|  |  | Data masking and data encryption method | SME/DB Admin | Naren | Reuse for now | 2019-07-31 | 2019-08-02
2 | Pattern Matching |  |  |  | Naren/Magesh |  | 2019-07-24 | 2019-08-30
|  | Pattern Identification | Define Patterns by Country, Product and other variables |  | Magesh | WIP | 2019-07-24 | 2019-08-30
|  |  | Identify & Match Patterns from Production cut - Production Data Analysis Engine | DB Access and Schema for all countries. Automation Team Support (Gopi & Gopi). Dependency on On-boarding & Laptop | Naren | Planned | 2019-08-12 | 2019-08-30
|  | Pattern Coverage | Identify & publish pattern coverage from Production cut (Incremental) |  | Naren/Magesh | Planned | 2019-08-30 | 2019-09-03
3 | Data Extraction Engine |  |  |  | Naren |  | 2019-07-31 | 2019-09-05
|  | Data Filtering | Build Data Filter for testing |  | Naren | Planned | 2019-08-12 | 2019-09-05
|  |  | Extact Data from production cut to RARE DB |  | Naren | Planned | 2019-08-12 | 2019-09-05
|  | Data Translation | Define Translation rules and conditions |  | Naren | Planned | 2019-07-31 | 2019-08-06
4 | Stubs/Mocks |  |  |  | Renish |  | 2019-07-31 | 2019-09-12
|  | Stubs for Interfaces | Identify interfaces and Protocols to stub/mock and Set up all pre-requisites for Stubs | Dev and Func Team of STS and DOTOPAL, EDMI Support for Pass - Madesh | Renish | WIP | 2019-07-31 | 2019-08-09
|  |  | Create Stubs | Environment, Collection points and access, EDMI connectivity with pass through, Creation of RARE Database | Renish | WIP | 2019-08-12 | 2019-09-12
5 | RARE Engine |  |  |  | Naren | Planned | 2019-07-26 | 2019-09-16
|  | Automation scripts for Data Push | Framework Design and Development |  | Naren | WIP | 26-Jull-19 | 2019-09-16
|  | Data matching | Extract transaction outputs & match against Test Production output |  | Naren | Planned | 2019-08-20 | 2019-09-16
|  | Schema Validation | Verify Test DB tables for Data type, Data length | Expected Schema Definitions and Rules | Naren | Planned | 2019-08-20 | 2019-09-16
|  | DQ Check | Validation for critical data elements | CDE details to be provided by STS and DOTOPAL team (Vinod Balaji & Madesh) | Naren | Planned | 2019-08-20 | 2019-09-16
|  | Reports | Test Summary - #Transactions Input, #Matches, #UnMatched Count |  | Naren | Planned | 2019-08-25 | 2019-09-16
|  |  | Pattern coverage - No of products, workflows tested using producton cut |  | Naren | Planned | 2019-08-25 | 2019-09-16
|  |  | Transaction coverage - No of critical scenarios tested using production cut |  | Naren | Planned | 2019-08-25 | 2019-09-16
|  |  | Mismatch Data Report |  | Naren | Planned | 2019-08-25 | 2019-09-16
6 | RARE Execution |  |  |  | Naren |  | 2019-09-16
|  | Dry Run | Dry Run 1 | Analysis Engine, Extraction Engine and RARE Engine | Naren | Planned | 2019-09-16 | 2019-09-18
|  |  | Dry Run 2 | Analysis Engine, Extraction Engine and RARE Engine | Naren | Planned | 2019-09-19 | 2019-09-23
|  |  | Continuous Improvements/Corrective Actions |  | Naren |  | 2019-09-24 | 2019-09-30
|  | Pilot Run | Test Run of Production Replay of DOTOPAL | Analysis Engine, Extraction Engine and RARE Engine | Naren | Planned | 2019-10-01 | 2019-10-08
|  |  | Test Run of Production Replay of STS | Analysis Engine, Extraction Engine and RARE Engine | Naren | Planned | 2019-10-09 | 2019-10-15
|  |  | Continuous Improvements |  | Naren | Planned | 2019-10-15 | 2019-10-22
|  | Full Fledged Run | Production Replay - Runs Week on Week with continuous focus on improvements |  | Naren | Planned | 2019-10-23
| CRITICAL DEPENDENCY |  | On-boarding of Team, their Laptops and Work Space
Recommended Environment for RARE Automation
Two Linux boxes
| 1 Box : | Data pre-processing, staging
| 2 Box : | Execution
PT Environment for STS and DOTOPAL
EDMI Connectivity with Pass through
RARE DB in an environment
Top Assumptions
Only model countries will be taken into consideration for RARE Testing in this phase. It is expected to be 8 countries.
Initially will provide simple reports, later a detailed Dashboard will be built to showcase the pattern coverages in production and in testing
A server with ELK or influx database to maintain automation data - Installation of Graphana or Kibana
STS & DOTOPAL testing team will take care of getting Production dump from the production support team and the same shall be deployed in the test Environment
Any production logs requirement from production to test environment will be provided by STS & DOTOPAL upon request
STS & DOTOPAL shall provide support if any reusability components that can be integrated into Maveric Solution

## Plan with Sub-Acitivity
# | Solution Component | Sub Components | Activity | Sub- Activity | Critical Dependency | Owner | Current Status | Target Start Date | Target End Date
1 | Production Dump Analysis
|  | Data Collection | Analyze Data Collection Points | Discuss and understand current data dump request and extraction process | Automation Team (Gopi Kannan & Gopi Murugan) | Naren | Planned | 2019-07-31 | 2019-08-06
|  |  |  | Discuss with SME about the touch points and liaise with developers | SPOC for Dev Team and Contacts (Ram to get SPOC to initiate the work) | Naren
|  |  |  | Obtain Table Details and Structure for data dump request | Dev/DB Admin
|  |  |  | Group Model Countries and identify for which country need to obtain production datadump | Automation Team (Gopi Kannan & Gopi Murugan)
|  |  | Define Data Collection Points | Define data collection parameters(If required) |  |  | Planned | 2019-08-05 | 2019-08-16
Data Collection Scripts(If Required)
|  | Data Masking | Understand PII fields | Discuss with SME and Understand PII fields across tables for STS and DOTOPAL | SME Support - DOTOPAL and STS | Naren | Reuse for now | 2019-07-31 | 2019-08-02
|  |  | Understanding of masking/data encryption | Discuss with SME/Developer/DB Admin and understand masking approach and practice | SME/DB Admin |  | Reuse for now | 2019-07-31 | 2019-08-02
Identify fields across tables to mask the data (TBD)
2 | Pattern Matching |  |  |  |  | Magesh | WIP |  | 2019-08-30
|  | Pattern Identification | Define Patterns by Country, Product and other variables | Product Identification | STS and DOTOPAL SME's |  | Completed
|  |  |  | Workflow and Sub-workflow Identification |  |  | WIP |  | 2019-07-30
|  |  |  | Scenario Identification (?) TBD with Vidhu |  | Magesh | WIP |  | 2019-08-14
|  |  |  | Other Critical Variables of Pattern |  |  | Planned | 2019-08-16
|  |  | Identify & Match Patterns from Production cut(Scripts) |  | DB Access and Schema for all countries. Automation Team Support (Gopi & Gopi). Dependency on On-boarding & Laptop | Naren | Planned | 2019-07-31
|  |  |  | Identify table details for Products, workflow and sub-workflow for STS and DOTOPAL | Pattern Identification
Building Scripts using SQL and Java Code
Run the script and verify the patterns
Develop DashBoard for Pattern showcasing
|  | Pattern Coverage | Identify & publish pattern coverage from Production cut (Incremental) |  |  | Naren | Planned | 2019-08-09
Run the Scripts and Extract the patterns
Publish the pattern coverage report
3 | Data Segregation |  |  |  |  | Naren | Planned | 2019-08-09
|  | Data Filtering | Build Data Filter for testing
Identify filters for data sub-setting
|  | Data Translation | Define Translation rules and conditions |  |  | Naren | Completed
Identify fields to translate data
|  |  | Implement Data Translation |  |  |  | Planned | 2019-08-20
4 | Stubs/Mocks
|  | Stubs for Interfaces | Identify interfaces and Protocols to stub/mock |  | Dev and Func Team of STS and DOTOPAL | Renish | WIP |  | 2019-07-26
|  |  |  | Understand the Interfaces and Protocols for STS and DOTOPAL | Dev and Func Team of STS and DOTOPAL
|  |  |  | EDMI Connectivity Pass Through for STS and DOTOPAL (Dedicated Queue/Topics for Automation) | Madesh/EDMI Team
Configuring the End Points in STS and DOTOPAL to point to Stub
Obatin an Linux Box for Automation Tool Environment
|  |  | Create Stubs |  | Environment, Collection points and access, EDMI connectivity with pass through, Creation of RARE Database | Renish | WIP |  | 2019-08-16
Develop Stubs for JMS WebMethods
Develop Stubs for MQ
Develop Stub for API
Deploying Stub in an Automation Tool Environment
Dry run to check the stubs
5 | RARE Engine | [5 empty] | Planned | NA
|  | Automation scripts for Data Push | Create automation scripts to push data to SUT |  |  |  | WIP | 2019-08-31
|  | Data matching | Extract transaction outputs & match against Test Production output |  |  |  | Planned | 2019-08-20
|  | Schema Validation | Verify Test DB tables for Data type, Data length |  | Expected Schema Definitions and Rules |  | Planned | 2019-08-20
|  | DQ Check | Validation for critical data elements |  | CDE details to be provided by STS and DOTOPAL team (Vinod Balaji & Madesh) |  | Planned | 2019-08-20
|  | Reports | Test Summary - #Transactions Input, #Matches, #UnMatched Count |  |  |  | Planned | 2019-08-25
|  |  | Pattern coverage - No of products, workflows tested using producton cut |  |  |  | Planned | 2019-08-25
|  |  | Transaction coverage - No of critical scenarios tested using production cut |  |  |  | Planned | 2019-08-25
|  |  | Mismatch Data Report |  |  |  | Planned | 2019-08-25
6 | RARE Execution
|  | Dry Run | Dry Run 1 |  |  |  | Planned | 2019-09-02
|  |  | Dry Run 2 |  |  |  | Planned | 2019-09-04
|  | Pilot Run | Test Run of Production Replay of DOTOPAL |  |  |  | Planned | 2019-10-01
|  |  | Test Run of Production Replay of STS |  |  |  | Planned | 2019-10-08
|  | Full Fledged Run | Production Replay - Runs Week on Week with continuous focus on improvements |  |  |  | Planned | 2019-10-16
Recommended Architecture
Two Linux boxes
|  | 1 Box : | Data pre-processing, staging
|  | 2 Box : | Execution
Separate STS and DOTOPAL Environment
EDMI Connectivity with Pass through
RARE DB in an environment
Assumptions
Only model countries will be taken into consideration for RARE Testing.
No User friendly dashboards, however there will
Note on H17: Ananthakrishnan, Ramachandran: Vidhu to define Scenario