## Sheet1
# | Solution Component | Sub Components | Activity | Critical Dependency | Owner | Current Status | Target Date | Target Start Date | Target End Date
1 | Production Dump Analysis | [6 empty] | 2019-07-31 | 2019-08-16
|  | Data Collection | Analyze Data Collection Points | Automation Team (Gopi Kannan & Gopi Murugan) SPOC for Dev Team and Contacts (Ram to get SPOC to initiate the work) Dependency on On-boarding & Laptop | Naren | Planned |  | 2019-07-31 | 2019-08-06
|  |  | Define Data Collection Points |  | Naren | Planned |  | 2019-08-05 | 2019-08-16
|  | Data Masking | Understand PII fields | SME Support - DOTOPAL and STS | Naren | Reuse for now |  | 2019-07-31 | 2019-08-02
|  |  | Understanding of masking/data encryption | SME/DB Admin | Naren | Reuse for now |  | 2019-07-31 | 2019-08-02
2 | Pattern Matching |  |  |  | Magesh | WIP | 2019-08-30 | 2019-07-24 | 2019-08-30
|  | Pattern Identification | Define Patterns by Country, Product and other variables |  | Magesh |  |  | 2019-07-24 | 2019-08-30
|  |  | Identify & Match Patterns from Production cut - Production Data Analysis Engine | DB Access and Schema for all countries. Automation Team Support (Gopi & Gopi). Dependency on On-boarding & Laptop | Naren | Planned |  | 2019-08-12 | 2019-08-30
|  | Pattern Coverage | Identify & publish pattern coverage from Production cut (Incremental) |  | Naren | Planned |  | 2019-08-30 | 2019-09-03
3 | Data Extraction Engine |  |  |  | Naren | Planned |  | 2019-07-31 | 2019-09-05
|  | Data Filtering | Build Data Filter for testing |  | Naren |  |  | 2019-08-12 | 2019-09-05
|  |  | Extact Data from production cut to RARE DB |  | Naren |  |  | 2019-08-12 | 2019-09-05
|  | Data Translation | Define Translation rules and conditions |  | Naren | Completed |  | 2019-07-31 | 2019-08-06
4 | Stubs/Mocks
|  | Stubs for Interfaces | Identify interfaces and Protocols to stub/mock and Set up all pre-requisites for Stubs | Dev and Func Team of STS and DOTOPAL, EDMI Support for Pass - Madesh | Renish | WIP | 2019-07-26 | 2019-07-31 | 2019-08-09
|  |  | Create Stubs | Environment, Collection points and access, EDMI connectivity with pass through, Creation of RARE Database | Renish | WIP | 2019-08-16 | 2019-08-12 | 2019-09-12
5 | RARE Engine |  |  |  |  | Planned |  | NA
|  | Automation scripts for Data Push | Framework Building |  |  | WIP |  |  | 2019-09-15
|  | Data matching | Extract transaction outputs & match against Test Production output |  |  | Planned |  | 2019-08-20
|  | Schema Validation | Verify Test DB tables for Data type, Data length | Expected Schema Definitions and Rules |  | Planned |  | 2019-08-20
|  | DQ Check | Validation for critical data elements | CDE details to be provided by STS and DOTOPAL team (Vinod Balaji & Madesh) |  | Planned |  | 2019-08-20
|  | Reports | Test Summary - #Transactions Input, #Matches, #UnMatched Count |  |  | Planned |  | 2019-08-25
|  |  | Pattern coverage - No of products, workflows tested using producton cut |  |  | Planned |  | 2019-08-25
|  |  | Transaction coverage - No of critical scenarios tested using production cut |  |  | Planned |  | 2019-08-25
|  |  | Mismatch Data Report |  |  | Planned |  | 2019-08-25
6 | RARE Execution
|  | Dry Run | Dry Run 1 |  |  | Planned |  | 2019-09-02
|  |  | Dry Run 2 |  |  | Planned |  | 2019-09-04
|  | Pilot Run | Test Run of Production Replay of DOTOPAL |  |  | Planned |  | 2019-10-01
|  |  | Test Run of Production Replay of STS |  |  | Planned |  | 2019-10-08
|  | Full Fledged Run | Production Replay - Runs Week on Week with continuous focus on improvements |  |  | Planned |  | 2019-10-16
Recommended Architecture
Two Linux boxes
|  | 1 Box : | Data pre-processing, staging
|  | 2 Box : | Execution
Separate STS and DOTOPAL Environment
EDMI Connectivity with Pass through
RARE DB in an environment
Assumptions
Only model countries will be taken into consideration for RARE Testing in this phase. It is expected to be 8 countries
No User friendly UI dashboards, however results will be shown in a readable format like excel or HTML
A server with ELK or influx database - Installation of Graphana or Kibana